## 11_07_2024
Gunaseelan M					Completed
09/07/2024					Not Completed
				In progress

				RBA_Power Status tracker Thoothukudi
				Handover
S.No	Project Name	Capacity	Location	AD/ED	PLDF	Material availability	Hardware	Software(iGate)	Grafana screen configuration	Monthly & Yearly Report	FAT	Delivery	Data in Cloud influx	Internet configuration(VPN)	Portal screens manual	Training
1	LNGSE	1MW	Thoothukudi	OLD Plants Completed
2	SBM	1MW
3	KAS-1	2MW
4	KAS-2	2MW
5	KAS-3	2MW
6	SDM	1MW
7	ENCEE	1MW
8	VPML	2MW
9	NISWIN_ENTERPRISES	1MW
10	SHANTHI_FEEDS PVT LTD	2MW
11	MDP	1MW
12	TMS	1MW
13	BESTICH	1MW
14	LOVELY	1MW
15	RUDHRANS_POWER	1MW
16	SDM-2	1MW

				RBA_Power Status tracker Trichy
17	NATURA POWER	2MW	Trichy
18	BESTICH-2	1MW
19	SELAM Sri KRISHNA CONSTRUCTION CO PVT LTD	1MW
20	SHEELA CLINIC	1MW
21	MANCHUNADHA	3MW
22	CENTURY	2MW